## Plan
30-day implementation planner
Week | Action | Owner | Status | Review date | Evidence
1 | Observe a representative manual baseline. |  | Not started
1 | Choose one task and record frequency, minutes and exceptions. |  | Not started
1 | Name the owner and reviewer; define trigger, sources and output. |  | Not started
1 | Agree prohibited actions, acceptance tests and rollback. |  | Not started
2 | Use approved or anonymized representative examples. |  | Not started
2 | Test missing fields, duplicates, changed records and out-of-scope requests. |  | Not started
2 | Check source accuracy, permissions and access removal. |  | Not started
2 | Give each defect an owner and retest date. |  | Not started
3 | Compare drafts with the manual process without duplicate live actions. |  | Not started
3 | Log corrections, errors, review time and unresolved cases. |  | Not started
3 | Check stop events and handoff; pause on prohibited actions. |  | Not started
3 | Update exception estimates from observations. |  | Not started
4 | Compare the whole workload, including review effort. |  | Not started
4 | Adopt, narrow the scope or stop using agreed evidence. |  | Not started
4 | Record accepted scope, known limits and manual fallback. |  | Not started
4 | Name the pause owner, review dates and update triggers. |  | Not started

## Tests and decision
Acceptance tests and ownership
Scenario | Expected | Observed | Owner / retest
Complete normal input | Define before testing
Missing required field | Define before testing
Duplicate event | Define before testing
Canceled / changed record | Define before testing
No source / conflicting source | Define before testing
Permission-restricted request | Define before testing
Downstream failure | Define before testing
Decision: adopt / adjust / stop | Define before testing
Fallback and pause owner | Define before testing
Next review date | Define before testing